# Computer Design Project - Monte Carlo Simulation Analysis

Using Monte Carlo Simulation with 10,000 iterations

| Activity | Label | Immediate Predecessors | Min Duration | Avg Duration | Max Duration |
| --- | --- | --- | --- | --- | --- |
| Design | A | - | 16 | 21 | 26 |
| Build prototype | B | A | 3 | 6 | 9 |
| Evaluate equipment | C | A | 5 | 7 | 9 |
| Test prototype | D | B | 2 | 3 | 4 |
| Write equipment report | E | C, D | 4 | 6 | 8 |
| Write methods report | F | C, D | 6 | 8 | 10 |
| Write final report | G | E, F | 1 | 2 | 3 |