## Slide 1: Project Management: Computer Design
A project manager has come up with the following information for a computer design project. It involves the following activities, precedence relationships, and estimated durations for activity completion (in weeks):
Considering uncertainty, what do you estimate as the mean duration of the project?
Create a histogram to reflect the possible durations.
What forecasted completion time would you provide if you wanted a “95% service level.” (i.e., if you wanted a 95% chance of completing the project within that timeframe).
Create and submit a flexible, user-friendly Streamlit app that lets user answer these questions for this project, but can also be used to analyze any project! Using your tool, also submit a Word doc with your responses to A, B, and C.
Activity | Label | Immediate predecessors | Minimum duration | Average duration | Maximum duration
Design | A | - | 16 | 21 | 26
Build prototype | B | A | 3 | 6 | 9
Evaluate equipment | C | A | 5 | 7 | 9
Test prototype | D | B | 2 | 3 | 4
Write equipment report | E | C,D | 4 | 6 | 8
Write methods report | F | C,D | 6 | 8 | 10
Write final report | G | E,F | 1 | 2 | 3